## issues
Title | Additional Body Text | Label | Assignee | size
Manual Testing Indirect interfaces | Follow the directions at: * https://developer.mantidproject.org/Testing/Indirect/DataReductionTests.html |  | cailafinn, thomashampson, MohamedAlmaki, adriazalvarez
Manual Testing Inelastic interfaces | Follow the directions at: * https://developer.mantidproject.org/Testing/Inelastic/DataAnalysisTests.html * https://developer.mantidproject.org/Testing/Inelastic/DataManipulationTests.html |  | cailafinn, thomashampson, MohamedAlmaki, adriazalvarez
Manual Testing Documentation | Check Online Docs and the Qt-help docs built into MantidWorkbench (from the help droppdown menu) * Algorithm, fit, concept and api pages should be generated * Algorithm dialog snapshots should appear on algorithm pages in offline help * Math formulae should appear on algorithm pages in offline help * workflow diagrams should appear on algorithm pages in offline help You may wish to use this script ( [OpenMostDocumentationForTesting.py](https://github.com/mantidproject/mantid/blob/master/tools/scripts/OpenMostDocumentationForTesting.py) ) to open all the online docs pages! |  | jclarkeSTFC, GuiMacielPereira, rbauststfc, warunawickramasingha
Manual Testing Workbench Group 1- 4 | https://developer.mantidproject.org/Testing/Core/Core.html |  | jhaigh0, SilkeSchomann, sf1919
Manual Testing Muon | See instructions at: https://developer.mantidproject.org/Testing/MuonAnalysis_test_guides/index.html |  | cailafinn, thomashampson, MohamedAlmaki, adriazalvarez
Manual Testing TOFConverter | Make sure that inputs and outputs work sensibly, stress test with some bad inputs (e.g. letters in a numeric input) https://docs.mantidproject.org/interfaces/utility/TOF%20Converter.html |  | jclarkeSTFC, GuiMacielPereira, rbauststfc, warunawickramasingha
Manual Testing FilterEvents | https://docs.mantidproject.org/interfaces/utility/Filter%20Events.html |  | jhaigh0, SilkeSchomann, sf1919
Manual Testing Engineering Diffraction | https://developer.mantidproject.org/Testing/EngineeringDiffraction/EngineeringDiffractionTestGuide.html |  | jclarkeSTFC, GuiMacielPereira, rbauststfc, warunawickramasingha
Manual Testing Sample Transmission calculator | Make sure that inputs and outputs work sensibly, stress test with some bad inputs (e.g. letters in a numeric input) See https://docs.mantidproject.org/interfaces/general/Sample%20Transmission%20Calculator.html |  | jclarkeSTFC, GuiMacielPereira, rbauststfc, warunawickramasingha
Manual Testing ISIS Reflectometry | http://developer.mantidproject.org/Testing/ReflectometryGUI/ReflectometryGUITests.html |  | jclarkeSTFC, GuiMacielPereira, rbauststfc, warunawickramasingha
Manual Testing ISIS SANS | https://developer.mantidproject.org/Testing/SANSGUI/ISISSANSGUITests.html |  | jhaigh0, SilkeSchomann, sf1919
Manual Testing Live Data ISIS | https://developer.mantidproject.org/Testing/LiveData/LiveDataTests.html |  | jclarkeSTFC, GuiMacielPereira, rbauststfc, warunawickramasingha
Manual Testing Mantid Basics Course | * Check the Qt-help docs, built into Workbench, against the online documentation * Open up the basic course: http://docs.mantidproject.org/tutorials/mantid_basic_course/index.html#mantid-basic-course * Check that the information and exercises are up to date and work in the Workbench release candidate |  | jhaigh0, SilkeSchomann, sf1919
Manual Testing M-slice | https://developer.mantidproject.org/Testing/Direct/MSliceTestGuide.html |  | jclarkeSTFC, GuiMacielPereira, rbauststfc, warunawickramasingha
Manual Testing Project Recovery | http://developer.mantidproject.org/Testing/ErrorReporter-ProjectRecovery/ProjectRecoveryTesting.html |  | jhaigh0, SilkeSchomann, sf1919
Manual Testing Error Reporter | http://developer.mantidproject.org/Testing/ErrorReporter-ProjectRecovery/ErrorReporterTesting.html |  | cailafinn, thomashampson, MohamedAlmaki, adriazalvarez
Manual Testing Sliceviewer | https://developer.mantidproject.org/Testing/SliceViewer/SliceViewer.html |  | cailafinn, thomashampson, MohamedAlmaki, adriazalvarez
Manual Testing Fit Script Generator | https://docs.mantidproject.org/nightly/interfaces/general/Fit%20Script%20Generator.html |  | cailafinn, thomashampson, MohamedAlmaki, adriazalvarez
Manual Testing ALF | https://developer.mantidproject.org/Testing/Direct/ALFViewTests.html |  | cailafinn, thomashampson, MohamedAlmaki, adriazalvarez

## assignees
Login | No Assigned
cailafinn | 7
thomashampson | 7
MohamedAlmaki | 7
adriazalvarez | 7
jclarkeSTFC | 7
GuiMacielPereira | 7
rbauststfc | 7
warunawickramasingha | 7
jhaigh0 | 5
SilkeSchomann | 5
sf1919 | 5